## Jira-2
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Priority | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved in v1.1? | Description | Comment
1.1 13-MFT: Dollar sign missing from the cash withdrawal | A1-24 | 10023 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-06 21:58 | 2023-07-06 21:58 | 2023-07-07 10:13 | N | Function being tested: Withdrawal: System asks customer to choose a dollar amount to withdraw * Initial State: Menu of account types is being displayed * Detailed steps to reproduce: Enter cash withdrawal amount * Expected Outcome: System displays a menu of possible withdrawal amounts * The actual outcome: $60 figure is missing dollar sign amount | 06/Jul/23 9:48 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1.
36-MFT: Transaction inquiry fails after entering invalid PIN | A1-22 | 10021 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-06 21:20 | 2023-07-06 21:20 | 2023-07-06 22:25 | N | Function being tested: Invalid PIN Extension: Customer is asked to reenter PIN, Correct re-entry of PIN is accepted * Initial State: Customer is asked to reenter PIN * Detailed steps to reproduce: Entering incorrect pin then trying to perform inquiry * Expected Outcome: Customer is asked to re-enter PIN * The actual outcome: Cannot attempt to perform an inquiry transaction after entering an incorrect PIN | 06/Jul/23 9:48 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1.
39/40-MFT: PIN fails re-entering valid PIN after incorrect attempt | A1-21 | 10020 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Low | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-06 21:16 | 2023-07-06 22:26 | 2023-07-06 22:25 | N | Function being tested: Invalid PIN Extension: Customer is asked to reenter PIN, Correct re-entry of PIN is accepted * Initial State: Customer is asked to re-enter PIN * Detailed steps to reproduce: Entering an incorrect PIN, then re-entering a valid PIN * Expected Outcome: Customer asked to perform a transaction * The actual outcome: Customer asked to re-enter PIN after the correct PIN was entered. | 06/Jul/23 9:48 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1.
34-MFT: System performs a legitimate inquiry transaction incorrectly | A1-20 | 10019 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-06 21:07 | 2023-07-06 21:47 | 2023-07-06 22:11 | Y | Function being tested: Inquiry: System performs a legitimate inquiry transaction properly * Initial State: System is displaying menu of account types * Detailed steps to reproduce: Check balance inquiry * Expected Outcome: System prints a correct receipt showing correct balance; System records transaction correctly in the log (showing both message to the bank and approval back) * The actual outcome: The receipt information is incorrect, it should say inquiry instead of transfer | 06/Jul/23 9:14 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
3-MFT: System output should demonstrate that connection | A1-16 | 10015 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-06 20:33 | 2023-07-06 21:48 | 2023-07-06 21:06 | N | Function being tested: System Startup: Connection to the bank is established * Initial State: System has just been turned on * Detailed steps to reproduce: Enter card, enter valid card details * Expected Outcome: System output should demonstrate that a connection has been established to the Bank * The actual outcome: No system output message to demonstrate that connection has been established | 06/Jul/23 8:57 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1
Invalid keyboard input crashing program | A1-15 | 10014 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:28 | 2023-07-06 22:16 | 2023-07-06 19:40 | N | Function being tested: Test keyboard input for all transaction types. * Initial State: Enter card, Enter valid card and pin, user prompted what they want to do * Detailed steps to reproduce: Click on any input outside the bounds of the option (ie. 5) * Expected Outcome: No action occurs * The actual outcome: Program crashes | 06/Jul/23 10:16 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1.
"Unknown Error" when checking money market balance | A1-14 | 10013 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:28 | 2023-07-06 22:14 | 2023-07-06 20:58 | Y | Function being tested: Test balance inquiry for a invalid/valid account. * Initial State: ATM display is prompting user to select an account to check balance inquiry for money market * Detailed steps to reproduce: Enter card, Enter valid card and pin, check balance inquiry, select money market * Expected Outcome: Displays to the user "Unknown Error" * The actual outcome: Display to the user the amount of cash in the money market | 06/Jul/23 10:14 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Receipt showing wrong card number after fund transfer | A1-13 | 10012 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:27 | 2023-07-06 22:19 | 2023-07-06 22:18 | N | Function being tested: Withdrawal: System performs a legitimate withdrawal transaction properly * Initial State: System is displaying the menu of withdrawal amounts * Detailed steps to reproduce: Perform any legitimate withdrawal with card 1 * Expected Outcome: System dispenses this amount of cash; System prints a correct receipt showing amount and correct updated balance; System records transaction correctly in the log (showing both message to the bank and approval back) * The actual outcome: Expected outcomes are achieved, except card number is displayed as 2 instead of 1 in the receipt | 06/Jul/23 10:13 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1.
Valid transfer values not updating correctly | A1-12 | 10011 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:27 | 2023-07-06 22:08 | 2023-07-06 21:00 | Y | Function being tested: Test successful transfer between two valid accounts. * Initial State: Transfer between Checking to Savings confirmed as successful * Detailed steps to reproduce: Enter card, Enter valid card and pin, transfer funds, select from savings to checking, transfer $50 * Expected Outcome: The values should be updated correctly savings decreases by $50 and checking increases by $50 * The actual outcome: The values should are incorrectly updated; savings decreases by $49.50 and checking increases by $49.50 | 06/Jul/23 10:08 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;The value is fixed. See [https://meng-seng637.atlassian.net/browse/A1-19¦https://meng-seng637.atlassian.net/browse/A1-19¦smart-link].
Deposit amount response does not match with input | A1-11 | 10010 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:26 | 2023-07-06 21:49 | 2023-07-06 22:21 | N | Function being tested: Test deposit to all the valid accounts * Initial State: ATM display is prompting user to deposit amount into checking account * Detailed steps to reproduce: Enter valid card details, deposit into checking, deposit $20 * Expected Outcome: Message for success and checking account increases total balance by $20 * The actual outcome: Message for success and checking account increases total balance by $10 | 06/Jul/23 9:19 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1. Different outcome at 1.1: The system recorded the transaction incorrectly, deposited $20, showed up as $19.9
Program freeze when performing multiple withdrawals | A1-10 | 10009 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:25 | 2023-07-06 22:06 | 2023-07-06 22:06 | Y | Function being tested: Test successful and insufficient balance cash withdrawal from valid savings, checking, and money market accounts * Initial State: ATM display informs user of amount of cash to withdraw after a couple withdraw transactions have already been completed * Detailed steps to reproduce: Enter valid card details, enter a couple valid withdrawals from chequing account, attempt to withdraw any valid amount * Expected Outcome: Withdraw the cash for valid withdrawals * The actual outcome: Program freezes and the ATM display no longer responds to the buttons | 06/Jul/23 10:06 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Withdraw values are $20 greater than advertised | A1-9 | 10008 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:25 | 2023-07-06 21:57 | 2023-07-05 23:30 | Y | Function being tested: Test successful and insufficient balance cash withdrawal from valid savings, checking, and money market accounts * Initial State: ATM display informs user of amount of cash to withdraw * Detailed steps to reproduce: Enter valid card details, enter withdraw cash from chequing account, withdraw any valid amount * Expected Outcome: If the withdrawal is valid, withdraw that exact amount from the bank account * The actual outcome: The system seems to withdraws $20 more than the advertised value in the ATM display (ie. $20 withdrawal withdraws $40) | 06/Jul/23 9:57 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Invalid response when withdrawing balance greater than current balance ($200) | A1-8 | 10007 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 23:24 | 2023-07-06 21:57 | 2023-07-06 20:58 | Y | Function being tested: Test successful and insufficient balance cash withdrawal from valid savings, checking, and money market accounts * Initial State: ATM display informs user of amount of cash to withdraw * Detailed steps to reproduce: Enter valid card details, enter withdraw cash from chequing account, withdraw $200 (current balance is $100) * Expected Outcome: Tells user that the withdraw amount is greater than the chequing balance and fail the transaction * The actual outcome: Withdraws $20 from the account as a successful transaction | 06/Jul/23 9:57 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Program freezes when invalid pin is entered | A1-7 | 10006 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Jash Dubal | 615cdf80d9820f0070b573c7 | Jash Dubal | 615cdf80d9820f0070b573c7 | 2023-07-05 22:27 | 2023-07-06 21:49 | 2023-07-06 20:58 | Y | Function being tested: Test Valid Invalid Card: * Initial State: Prompt user with entering card information * Detailed steps to reproduce: Insert card, Enter pin of 42 in initial state, Click Enter * Expected Outcome: Insert card, Enter pin of 42 in initial state, System detects this as invalid card and prompts you to enter another card * The actual outcome: When Enter is hit, the simulated ATM display informs user that the card number is invalid and prompt them to enter another one | 06/Jul/23 9:57 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Wrong account details displaying: Money Market | A1-5 | 10004 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | 2023-07-05 22:15 | 2023-07-06 21:56 | 2023-07-07 10:13 | Y | * The function being tested: Test balance inquiry Money market account option * The initial state of the system: ATM display is prompting user to select an account to check balance inquiry * Detailed steps to reproduce the defect/bug: select money market * The expected outcome: instead of the money market account option in balance inquiry, saving account should be an option * The actual outcome: the receipt prints out the balance of the saving account | 06/Jul/23 9:57 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Invalid account: Money Market | A1-4 | 10003 | Bug | To Do | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | 2023-07-05 22:11 | 2023-07-06 22:36 | 2023-07-07 10:09 | N | * The function being tested: Testing valid accounts types for savings, checking, transfer * The initial state of the system: ATM displaying all transaction options * Detailed steps to reproduce the defect/bug: - select withdraw, select Money Market, select any withdrawal option, invalid account type - select deposit, select Money Market, select any deposit amount, invalid account type - select transfer, select Money Market, select saving/checking, type in the transfer amount, invalid account type * The expected outcome: money market account should not be an option when selecting withdrawal/deposit/transfer * The actual outcome: when selecting the money market option when selecting withdrawal/deposit/transfer and entered desired respective amounts, invalid account type message pops up | 06/Jul/23 9:54 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Defect still exists in version 1.1.
Cash Withdrawal: Selecting withdrawal amount | A1-3 | 10002 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | 2023-07-05 21:56 | 2023-07-06 21:51 | 2023-07-07 10:13 | Y | * The function being tested: Selection of withdrawal amounts * The initial state of the system: Withdraw transaction is selected from checking account, displaying amounts options * Detailed steps to reproduce the defect/bug: choose option 1 which is $20 * The expected outcome: the withdrawal amount selected should be withdrawn from the chosen account * The actual outcome: when picking option 1 ($20), withdraw amount of option 2 ($40) is withdrawn | 06/Jul/23 9:20 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1
Card Validation and PIN Verification: Test invalid card | A1-2 | 10001 | Bug | Done | A1 | a1 | software | Jash Dubal | 615cdf80d9820f0070b573c7 | Medium | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | Nikhil Naikar | 70121:7a7efa69-517c-4f53-989b-435e62e2b108 | 2023-07-05 21:40 | 2023-07-06 21:48 | 2023-07-07 10:13 | Y | * The function being tested: Testing invalid card number * The initial state of the system: system is on, prompt to enter card number * Detailed steps to reproduce the defect/bug: enter an invalid card number * The expected outcome: notify invalid card number was entered and go back to prompt for enter card number * The actual outcome: allowed to move on to prompt for pin, no error log message, screen is frozen | 06/Jul/23 9:18 PM;712020:06a21946-b185-48ed-9c99-bce58a4aa77d;Fixed in 1.1, invalid card message display after pin entered.
Notes: Teal rows indicate duplicate bugs found between exploratory and MFT